## Sheet1
Project Name : Blog Application
Sprint-1.0 |  | Date: 04-Jan-2024
# | +ve | ∆ | Action Item | Target Date | Responsible
1 | effective stand up meetings on daily basis enabling team to work efficiently | extra time spent on unnecessary features | tasks to be completed strictly based on priority assigned | Next Project | Team
2 | effective coordination and communication between the team members | issues faced initially to include fontawesome icons in the project | proper clarity could be obtained reading the detailed documentation | Next Project | Team
3 | Being supportive in fixing major bugs and errors | creating pull requests for minor changes | pull requested to be created only large chunks of changes instead | Next Project | Team