## Sheet1
Product Backlog
# | Features / Requirements - Level 1 | Features / Requirements - Level 2 | Release phase / Milestone | Priority | Status | Story Point Estimation
[6 empty] | Initial Estimation | Sprint 01
1 | REQ01-Home Page
|  | Header | Release-1 | P1 | Completed | 2 | 2
|  | Section-01 | Release-1 | P1 | Completed | 3 | 3
|  | Section-02 | Release-1 | P1 | Completed | 2 | 2
|  | Section-03 | Release-1 | P1 | Completed | 3 | 3
|  | Section-04 | Release-1 | P1 | Completed | 5 | 5
|  | Footer | Release-1 | P1 | Completed | 2 | 2
2 | REQ02-Hotel Listing
|  | Dynamic Loading of hotel list. | Release-1 | P2 | Completed | 7 | 7
|  | Toggling between hotel list pages. | Release-1 | P2 | Completed | 3 | 3
|  | popUp for hotel description. | Release-1 | P2 | Completed | 2 | 2
|  | Navigation to Particular Hotel's details page | Release-1 | P2 | Completed | 2 | 2
|  | Hotel Filtering to the desktop View | Release-1 | P2 | Completed | 7 | 6
|  | Hotel Filtering to the Mobile View | Release-1 | P2 | Completed | 5 | 5
|  | Hotel Filtering with the Functionality | Release-1 | P2 | Completed | 7 | 7
3 | REQ03-Hotel Details
|  | Dynamica Rendering the Section-1 | Release-1 | P3 | Completed | 7 | 7
|  | Embeded Goggle Map | Release-1 | P3 | Completed | 4 | 4
|  | About Hotel Section | Release-1 | P2 | Completed | 3 | 3
|  | Amenities Section | Release-1 | P2 | Completed | 3 | 3
|  | Room Options Section | Release-1 | P4 | Completed | 7 | 7
|  | popup for particular room options | Release-1 | P5 | Completed | 6 | 6
|  | Hotel Policies | Release-1 | P5 | Completed | 1 | 1
4 | REQ04-Checkout
|  | detailed hotel description- static view | Release-1 | P3 | Completed | 1 | 1
|  | detailed hotel description- static view | Release-1 | P3 | Completed | 1 | 1
|  | user credentials | Release-1 | P3 | Completed | 3 | 3
|  | checkin and checkout component | Release-1 | P3 | Completed | 1 | 1
|  | additional travellers details | Release-1 | P3 | Completed | 5 | 4
|  | booking summary | Release-1 | P3 | Completed | 2 | 2
|  | localstorage | Release-1 | P3 | Completed | 5 | 4
|  | increment/ decrement button | Release-1 | P3 | Completed | 1 | 1
5 | REQ05-Admin
|  | Login Page | Release-1 | P4 | Completed | 3 | 3
|  | Dashboard | Release-1 | P4 | Completed | 5 | 4
|  | LogOut | Release-1 | P5 | Completed | 2 | 2
110