## Sheet1
Sprint Backlog
Requirements | Task Id | Task description | Responsible team Memeber | Cumulative hours spent | Status (Not started / In Progress / Completed) | Hours of work remaining until completion
[7 empty] | Wed | Thu | Fri | Mon | Tue | Wed
[6 empty] | Day | 2023-12-27 | 2023-12-28 | 2023-12-29 | 2023-01-01 | 2023-01-02 | 2023-01-03
[6 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6
REQ01-Home Page
Header | US_01 | Header Section | Monika | 1 | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0
| US_02 | Navigation to Home Page | Monika | 1 | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0
Section-01 | US_03 | Section1 Section | Monika | 2 | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0
| US-04 | Navigation to hotel listing page | Monika | 1 | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0
section-02 | US_05 | common services provided by hotels | Suhas Indrigi | 1 | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0
| US_06 | general rating of past customers | Suhas Indrigi | 1 | completed | 1 | 1 | 0 | 0 | 0 | 0 | 0
Section-03 | US_07 | Featured Hotel | Monika | 4 | Completed | 4 | 0 | 3 | 1 | 0 | 0 | 0
| US_08 | Navigation to hotel listing page | Monika | 1 | Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0
Section-04 | US_09 | Testimonial Section | Mohammad Rooh Ullah | 4 | Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0
| US_10 | Toggling between testimonials | Mohammad Rooh Ullah | 1 | Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0
Footer | US_11 | Footer Section | Mohammad Rooh Ullah | 2 | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0
| US_12 | Navigation to Admin login. | Mohammad Rooh Ullah | 1 | Completed | 1 | 0 | 0 | 0 | 1 | 0 | 0
REQ02-Hotel Listing
Hotel List | US_13 | Loading the list of hotels from json. | Mohammad Rooh Ullah | 6 | Completed | 6 | 0 | 3 | 3 | 0 | 0 | 0
| US_14 | Toggling between the hotel list pages. | Mohammad Rooh Ullah | 3 | Completed | 3 | 0 | 0 | 3 | 0 | 0 | 0
| US_15 | PopUp showing the detailed description of selected hotel. | Mohammad Rooh Ullah | 2 | Completed | 2 | 0 | 0 | 1 | 1 | 0 | 0
| US_16 Navigation to Hotel-Details Page |  | Monika | 2 | Completed | 2 | 0 | 0 | 2 | 1 | 0 | 0
Filtering | US_17 | Hotel Type Filter | Jeevan | 3 | Completed | 3 | 1 | 1 | 0 | 1 | 0 | 0
| US_18 | Price Range Filter | Jeevan | 4 | Completed | 4 | 0 | 1 | 2 | 1 | 0 | 0
| US_19 | Popular type filter and rating Star Filter | Jeevan | 1 | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0
| US_20 | Customer Rating filter | Jeevan | 3 | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0
| US_21 | Ammenities Filter | Jeevan | 4 | Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0
| US_22 | Clear all Filter | Jeevan | 4 | Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0
| US_23 | Mobile view with Different design | Jeevan | 5 | Completed | 5 | 0 | 0 | 2 | 1 | 2 | 0
| US_24 | Pop Up Container in the mobile view | Jeevan | 2 | Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0
REQ03-Hotel Details
Hotel Details | US_25 | Dynamic View of Hotel Details Section1 | Monika | 7 | Completed | 7 | 0 | 0 | 3 | 4 | 0 | 0
| US_26 | Embeded Google Map | Monika | 2 | Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0
| US_27 | About the Hotel | Monika | 2 | Completed | 2 | 0 | 0 | 0 | 2 | 0 | 0
| US_28 | Amenities of the hotel | Monika | 2 | Completed | 2 | 0 | 0 | 0 | 2 | 0 | 0
| US_29 | Dynamic rendered the Room Option's Section of each hotel | Monika | 5 | Completed | 5 | 0 | 0 | 0 | 0 | 5 | 0
| US_30 | Dynamic Room options popup of each Rooms | Monika | 4 | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 4
| US_31 | Static Hotel Poliies Section | Monika | 1 | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 1
REQ04-Checkout
detailed hotel description- static view | US_32 | static view of detailed hotel description | Suhas Indrigi | 1 | completed | 2 | 0 | 1 | 0 | 0 | 0 | 0
detailed hotel description- static view | US_33 | dynamic view of detailed hotel description | Suhas Indrigi | 1 | completed | 2 | 0 | 0 | 0 | 0 | 0 | 1
user credentials | US_34 | form to collect user credentials | Suhas Indrigi | 3 | completed | 3 | 0 | 2 | 1 | 0 | 0 | 0
checkin and checkout dates | US_35 | component for obtaining user checkin and checkout dates | Suhas Indrigi | 1 | completed | 1 | 0 | 0 | 1 | 0 | 0 | 0
additional travellers details | US_36 | adding and removing the addtional travellers details dynamically | Suhas Indrigi | 4 | completed | 5 | 0 | 0 | 3 | 1 | 0 | 0
booking summary | US_37 | displaying the amount, checkin and checkout details to the customer | Suhas Indrigi | 2 | Completed | 2 | 0 | 0 | 0 | 1 | 1 | 0
localstorage | US_38 | inserting the user credentials into local storage | Suhas Indrigi | 4 | Completed | 5 | 0 | 0 | 0 | 2 | 2 | 0
increment/ decrement button | US_39 | ability for the user to increase/ decrease the number of rooms to be booked | Suhas Indrigi | 1 | completed | 1 | 1 | 0 | 0 | 0 | 0 | 0
REQ05-Admin
Login Page | US_40 | Admin login page | Mohammad Rooh Ullah | 3 | Completed | 3 | 0 | 0 | 0 | 2 | 1 | 0
Dashboard | US_41 | Admin Dashboard | Mohammad Rooh Ullah | 4 | Completed | 5 | 0 | 0 | 0 | 2 | 2 | 0
Logout Functionality | US_42 | Admin Logout Functionality | Mohammad Rooh Ullah | 2 | Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0

## Sheet3
|  | Ideal | Remaining
Tue | Day 0 | 42 | 42
Wed | Day 1 | 35 | 34
Thu | Day 2 | 28 | 29
Fri | Day 3 | 21 | 22
Mon | Day 4 | 14 | 11
Tue | Day 5 | 7 | 3
Wed | Day 6 | 0 | 0